## W1
PROJECT REPORT
Group | Group 4
Week | 05/09/2022 - 11/09/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Chooses project topic | Completed | Team come to an agreement of which topic should team choose for project
2 | Kicks off meeting | Completed | Meet up with team members
3 | Determine role of team members | Completed | Decide skills and strengths of each team member
5 | Analyze project requirements | Completed | Research information and rely on actual figures to predict usage needs
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Decides team rules and regulations | All Team | Sets out working rules and regulation upon agreements of everyone
2 | Brainstorm project ideas | All Team | Finds idea for project
3 | Brainstorm project ideas with the Instructor | All Team + Instructor(DuongTB) | Rules out which are good ideas and which are not
4 | Choose final project idea | All Team + Instructor(DuongTB) | Chooses final project idead
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Start planning for the web application project | 2022-01-15
2 | Start to design and make report | 2022-01-15
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAT74GjHA Author (2022-01-10 10:24:30) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C19: ====== ID#AAAAT74GjG8 Author (2022-01-10 10:24:30) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W2
PROJECT REPORT
Group | Group 5
Week | 10/01/2022 - 15/01/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Make project requirements | In Progress | Discussion from the info based on the actual needs of those involved in the isolation process
2 | Define coding language | Completed | Use java language
3 | Design function model for web application | Completed | Finish the ERD diagram and database
4 | Build Entity Relationship Diagram and database | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Team meeting and make the plan | All Team | Finish the plan for this week, set the deadline for team member
2 | Discuss and list requirements | All Team | Define specific requirements for each user object.
3 | Create ERD Diagram and Database | All Team | Discuss and choose the final database
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
Design screen function
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes